## Overview
COFFEE'D: EPISODE ONE "THE 1911"
Two-Night Shooting Schedule · 6:00 PM – 12:00 AM each night · Dates TBD
SHOOTING LOCATION
Location | Black Rifle Coffee Company: San Antonio (Bitters Rd)
Address | 180 W Bitters Rd, San Antonio, TX 78216
Phone | (210) 963-9660
Café hours | Open daily 5:30 AM – 8:00 PM (per BRCC location page)
Heads up | The café is open until 8:00 PM, so the first 2 hours of each night overlap business hours. Arrange a buyout or early close, or shoot Scene 1 (exterior) and prep only until 8:00 PM.
Source | https://caf.blackriflecoffee.com/locations/san-antonio
Writers | Nikki Howard & Brent Pella
DAY SUMMARY
Day | Focus | Setups | Screen time (sec) | Scenes
Day 1 | Front of House — Garrett Day | 20 | 122 | 1, 2, 7
Day 2 | Back of House | 27 | 234 | 4, 6, 5, 3
Total |  | 47 | 356
NOT ON THE CLOCK
Shot 2.9 | Title card: built in post / graphics. No shoot time.
Evan (V.O.) | Scene 7 phone dialogue: record separately and filter in post. Play a scratch track on set Day 1 for timing.
Optional pickup | Garrett sprints to his truck and peels out (in script, not on shot list). Grab at end of Day 1 if time allows.
Night for day | Scenes 1, 2 and 7 are written as DAY. Cover or light the café windows to read as daytime.
Prop weapons | Armorer on set Day 1. Cold-weapon check before the AK entrance. Notify the venue and neighbors, since a masked actor with a prop rifle will be visible through the windows.

## Shooting Schedule
Day | Start | End | Block (min) | Type | Scene | Shot | Location | Set / Area | I/E | Size | Angle | Movement | Lens | Rig | Cast | Screen time (sec) | Description | Notes
Day 1 | 18:00 | 18:15 | 15 | Crew |  |  | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | [8 empty] | 0 | Crew call · Load-in · Safety meeting | Cast to hair & makeup. Scene 1 has no cast, so camera rolls while talent preps.
Day 1 | 18:15 | 18:25 | 10 | Shot | 1 | 1.1 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Exterior: storefront & flagpole | EXT | Wide | Eye-level | Static | 24mm | Steady cam | — | 4 | The exterior of the Black Rifle Coffee cafe fills the frame, showing its entrance and outdoor seating area. The American flag is visible on a pole near the storefront. | Race the sun: get exteriors before last light.
Day 1 | 18:25 | 18:35 | 10 | Shot | 1 | 1.2 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Exterior: storefront & flagpole | EXT | Close-up | Low angle | Static | 50mm | Steady cam | — | 3 | The American flag waves back and forth on the pole in the breeze.
Day 1 | 18:35 | 18:45 | 10 | Shot | 1 | 1.3 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Exterior: storefront & flagpole | EXT | Medium | Eye-level | Slow push in | 35mm | Steady cam | — | 3 | The camera frames the Black Rifle Coffee logo on the cafe window.
Day 1 | 18:45 | 19:05 | 20 | Move |  |  | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | [8 empty] | 0 | Move inside · Light café for day interior | Cover or gel windows to sell daytime. Place 4 background customers in line.
Day 1 | 19:05 | 19:25 | 20 | Shot | 2 | 2.2 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Wide | Eye-level | Slow push-in | 24mm | Steady cam | 4 Bruce | 4 | A wide view of the cafe reveals military and Americana decor, with a short line of customers waiting at the counter and Bruce on a step stool working on a ceiling tile in the background. | Master. Background in line, Bruce on step stool.
Day 1 | 19:25 | 19:40 | 15 | Shot | 2 | 2.3 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Two-shot | Eye-level | Static | 35mm | Steady cam | 3 Lacey, 5 Garrett | 6 | At the counter, Garrett steps up in front of Lacey , who stands at the register facing him.
Day 1 | 19:40 | 19:55 | 15 | Shot | 2 | 2.5 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Over-the- shoulder | Eye-level | Static | 50mm | Steady cam | 5 Garrett | 4 | Over Garrett's shoulder, the customers in line behind him lean and crane their necks to look past him toward the counter. | Background reactions. Background wraps after this.
Day 1 | 19:55 | 20:15 | 20 | Shot | 2 | 2.4 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Medium | Eye-level | Static | 50mm | Steady cam | 3 Lacey, 5 Garrett | 10 | Lacey glances down toward Garrett's holstered pistol and then lifts her gaze back up to him with a dry expression.
Day 1 | 20:15 | 20:30 | 15 | Shot | 2 | 2.6 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Medium Close-up | Eye-level | Static | 65mm | Steady cam | 3 Lacey, 5 Garrett | 8 | Garrett narrows his eyes at Lacey, his expression tightening at the counter.
Day 1 | 20:30 | 20:40 | 10 | Shot | 2 | 2.8 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Medium | Low angle | Static | 40mm | Steady cam | 4 Bruce | 3 | On the step stool, Bruce pauses with his hands near the ceiling tile and turns his head toward the counter, his face showing concern.
Day 1 | 20:40 | 20:50 | 10 | Shot | 2 | 2.1 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Close-up | Eye-level | Static | 85mm | Steady cam | — | 3 | A wall clock above the cafe counter shows the time clearly. The frame holds on the clock face without revealing the rest of the room. | Insert: clock set to 9:11.
Day 1 | 20:50 | 21:05 | 15 | Shot | 2 | 2.7 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Close-up | High angle | Slow push-in | 60mm | Steady cam | 3 Lacey | 4 | A takeout cup on the counter fills the frame as Lacey writes on its side, revealing the words 'GARRETT (ARMED)'. | Insert: cup reads GARRETT (ARMED).
Day 1 | 21:05 | 21:35 | 30 | Meal |  |  | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | [8 empty] | 0 | Meal · 30 min
Day 1 | 21:35 | 21:45 | 10 | Crew |  |  | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | [8 empty] | 0 | Armorer briefing · Rehearse AK entrance | Cold-weapon check with all cast & crew. Notify neighbors / venue: masked actor with prop rifle visible through windows.
Day 1 | 21:45 | 21:55 | 10 | Shot | 7 | 7.1 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Medium wide | Eye-level | Static | 28mm | Steady cam | 1 Erica, 3 Lacey, 5 Garrett | 5 | Garrett strides in through the front door toward the counter, his pistol visible at his hip as Erica and Lacey stand waiting behind the register. | Clock reset to 9:59.
Day 1 | 21:55 | 22:07 | 12 | Shot | 7 | 7.2 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Two-shot | Eye-level | Static | 35mm | Steady cam | 1 Erica, 3 Lacey, 5 Garrett | 8 | Erica faces Garrett across the counter, hands lightly resting on the surface as she addresses him directly.
Day 1 | 22:07 | 22:17 | 10 | Shot | 7 | 7.3 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Medium | Eye-level | Slow push-in | 40mm | Steady cam | 1 Erica, 3 Lacey, 5 Garrett | 6 | Lacey steps forward from behind the counter holding an index card, glancing from Garrett to the wall clock as Erica gives her a small nudge. | Index card prop.
Day 1 | 22:17 | 22:37 | 20 | Shot | 7 | 7.4 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Wide | Eye-level | Quick handheld pan | 24mm | Handheld | 1 Erica, 2 J.D., 3 Lacey, 4 Bruce, 5 Garrett | 10 | Bruce bursts in through the back door with an AK raised, his posture aggressive as everyone near the counter recoils toward cover. | Bruce's entrance. Several takes; reset back door each time.
Day 1 | 22:37 | 22:49 | 12 | Shot | 7 | 7.5 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Medium | Eye-level | Slow push-in | 50mm | Steady cam | 1 Erica, 2 J.D., 3 Lacey, 4 Bruce, 5 Garrett | 7 | Everyone at the counter turns toward Garrett as he stands rigid with his hand hovering near his holster, eyes locked on Bruce’s rifle and lips moving in silent calculation.
Day 1 | 22:49 | 23:05 | 16 | Shot | 7 | 7.6 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Medium wide | Three-quarter rear | Slow tracking backward | 35mm | Steady cam | 4 Bruce, 5 Garrett | 9 | Garrett slowly raises both hands above his shoulders and walks backward toward the front door, keeping his gaze fixed on Bruce until he slips out of the shop. | Garrett backs out the front door.
Day 1 | 23:05 | 23:13 | 8 | Shot | 7 | 7.7 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Medium | Eye-level | Static | 40mm | Steady cam | 4 Bruce | 4 | Bruce now stands near the counter with his ski mask pushed up, looking toward the door with a puzzled expression as the rifle lowers slightly.
Day 1 | 23:13 | 23:23 | 10 | Shot | 7 | 7.8 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Medium | Eye-level | Static | 45mm | Steady cam | 3 Lacey | 5 | Lacey stoops to retrieve the fallen index card from the floor behind the counter, then tears it into small pieces over the trash can. | Multiple index cards for retakes.
Day 1 | 23:23 | 23:45 | 22 | Shot | 7 | 7.9 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Café floor & counter | INT | Medium wide | Eye-level | Slow push-in | 32mm | Steady cam | 1 Erica, 2 J.D., 3 Lacey, 4 Bruce | 16 | Erica stands at the counter with the store phone at her ear on speaker, her hand trembling slightly as Bruce, Lacey, and J.D. lean in around her to listen. | Play Evan's V.O. on speaker for timing.
Day 1 | 23:45 | 0:00 | 15 | Wrap |  |  | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | [8 empty] | 0 | Wrap · Armorer secures weapons · Load-out
Day 1 |  |  | 360 | Total |  | 20 | [9 empty] | 122 | Day 1 total: setups and screen time
Day 2 | 18:00 | 18:30 | 30 | Crew |  |  | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | [8 empty] | 0 | Crew call · Light counter set | Cast to hair & makeup. Bruce needs mop.
Day 2 | 18:30 | 18:43 | 13 | Shot | 4 | 4.1 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Behind the counter | INT | Medium Wide | Eye-level | Static | 28mm | Steady cam | 1 Erica, 2 J.D., 3 Lacey, 4 Bruce | 7 | Behind the counter, Erica stands in front of Lacey, J.D., and Bruce, gathering them into a loose huddle as Bruce holds an idle mop. Everyone stands in a relaxed lull, waiting for her to speak. | Master: team huddle.
Day 2 | 18:43 | 18:55 | 12 | Shot | 4 | 4.2 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Behind the counter | INT | Two-shot | Eye-level | Slow push-in | 35mm | Steady cam | 1 Erica, 2 J.D., 3 Lacey, 5 Garrett | 9 | The group remains clustered behind the counter, heads subtly shaking in unison as Erica addresses them about the gun, with their expressions shifting into animated debate.
Day 2 | 18:55 | 19:07 | 12 | Shot | 4 | 4.3 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Behind the counter | INT | Medium | Eye-level | Static | 40mm | Steady cam | 1 Erica, 2 J.D., 3 Lacey | 10 | The camera favors Lacey and J.D. across the counter as they trade barbs, with Erica slightly off to one side, listening tensely to their exchange.
Day 2 | 19:07 | 19:20 | 13 | Shot | 4 | 4.4 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Behind the counter | INT | Medium | Eye-level | Slow pan | 35mm | Steady cam | 1 Erica, 2 J.D., 3 Lacey, 4 Bruce | 14 | The frame tightens on Bruce near the counter, his mop paused on a single tile, as Erica turns toward him for support and the others look to him expectantly.
Day 2 | 19:20 | 19:28 | 8 | Shot | 4 | 4.5 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Behind the counter | INT | Close-up | Eye-level | Static | 50mm | Handheld | 1 Erica, 4 Bruce | 5 | A closer view frames Bruce from the chest up as Erica snaps at him, his posture stiffening and his expression tightening at the insult.
Day 2 | 19:28 | 19:39 | 11 | Shot | 4 | 4.6 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Behind the counter | INT | Medium Wide | Eye-level | Slow tracking | 32mm | Steady cam | 4 Bruce | 7 | Bruce slowly leans his mop against the counter, his face showing a small shift before he turns away and walks through the doorway into the back as the others watch. | Bruce exits to the back.
Day 2 | 19:39 | 19:50 | 11 | Shot | 4 | 4.7 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Behind the counter | INT | Medium | Eye-level | Slow push-in | 40mm | Steady cam | 1 Erica, 3 Lacey | 8 | Erica remains behind the counter, glancing toward the back door with a worried expression as Lacey gives a casual shrug and a cocky smile before walking away.
Day 2 | 19:50 | 20:05 | 15 | Move |  |  | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | [8 empty] | 0 | Move to break area
Day 2 | 20:05 | 20:17 | 12 | Shot | 6 | 6.1 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Break area | INT | Medium | Eye-level | Slow push-in | 35mm | Steady cam | 2 J.D. | 6 | J.D. stands at a whiteboard, writing a list under the heading about proposed courses of action. The numbered options fill the board in clear, block letters. | Whiteboard: PROPOSED COURSES OF ACTION.
Day 2 | 20:17 | 20:32 | 15 | Shot | 6 | 6.2 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Break area | INT | Two-shot | Eye-level | Static | 40mm | Steady cam | 1 Erica, 2 J.D., 3 Lacey, 4 Bruce | 14 | Lacey and Erica stand by the break area counter facing J.D., reacting differently to the options on the whiteboard. Lacey looks amused as Erica grows defensive and animated.
Day 2 | 20:32 | 20:47 | 15 | Shot | 6 | 6.3 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Break area | INT | Medium | Eye-level | Minor reframing | 35mm | Handheld | 1 Erica, 3 Lacey, 5 Garrett | 16 | Lacey hunches over a small table, scribbling on a napkin and then holding it up toward the others with a mischievous look. She repeatedly adjusts the wording as Erica reacts off to the side. | Napkins + marker for apology drafts.
Day 2 | 20:47 | 21:00 | 13 | Shot | 6 | 6.4 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Break area | INT | Medium | Eye-level | Slow pan | 35mm | Steady cam | 4 Bruce | 14 | Bruce enters the break area doorway peeling off yellow rubber gloves, his posture heavy and drained. The others at the table react with disgusted expressions as Bruce stares off, replaying what he just went through. | Yellow rubber gloves.
Day 2 | 21:00 | 21:15 | 15 | Shot | 6 | 6.5 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Break area | INT | Medium | Eye-level | Slow push-in | 32mm | Steady cam | 1 Erica, 2 J.D., 3 Lacey, 5 Garrett | 18 | J.D. rises slowly from his chair, looking past the others toward the whiteboard with sudden intensity. Lacey and Erica start to react before he cuts them off, and the group closes in around him as he lays out his idea.
Day 2 | 21:15 | 21:25 | 10 | Shot | 6 | 6.6 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Break area | INT | Medium | Eye-level | Static | 40mm | Handheld | 2 J.D., 4 Bruce | 10 | All three slowly turn their heads toward Bruce, who stands nearby mid-bite into a granola bar, frozen in confusion. He looks back at them uncertainly as J.D. presses him and he forces down the mouthful. | Granola bar. Bruce (Caleb) wraps after this.
Day 2 | 21:25 | 21:55 | 30 | Meal |  |  | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | [8 empty] | 0 | Meal · 30 min
Day 2 | 21:55 | 22:05 | 10 | Move |  |  | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | [8 empty] | 0 | Reset back room | Desk, syrup boxes, mini fridge, "SAFETY IS EVERYONE'S JOB" whiteboard, org chart with Erica's face.
Day 2 | 22:05 | 22:15 | 10 | Shot | 5 | 5.1 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Three- shot | Eye-level | Static | 35mm | Tripod | 1 Erica, 2 J.D., 3 Lacey, 4 Bruce | 7 | Lacey and J.D. sit across from Erica at a small table, facing her like an interview panel. They hold tense postures across the table from her. | Mostly tripod coverage, so these move fast.
Day 2 | 22:15 | 22:22 | 7 | Shot | 5 | 5.2 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium | Eye-level | Static | 50mm | Tripod | 1 Erica, 2 J.D., 3 Lacey | 5 | Erica leans forward over the table, gesturing in frustration toward Lacey and J.D.
Day 2 | 22:22 | 22:30 | 8 | Shot | 5 | 5.4 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium | Eye-level | Slow push-in | 50mm | Steady cam | 1 Erica, 2 J.D. | 7 | Erica turns toward J.D., bracing her hands on the edge of the table as she lays out her worries.
Day 2 | 22:30 | 22:36 | 6 | Shot | 5 | 5.3 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium | Eye-level | Static | 50mm | Tripod | 1 Erica, 2 J.D., 3 Lacey | 4 | J.D. sits rigidly in his chair, looking between Lacey and Erica with mounting concern.
Day 2 | 22:36 | 22:42 | 6 | Shot | 5 | 5.5 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium | Eye-level | Static | 50mm | Tripod | 1 Erica, 2 J.D. | 6 | J.D. leans back slightly in his chair, looking at Erica with dry skepticism.
Day 2 | 22:42 | 22:47 | 5 | Shot | 5 | 5.7 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium Close-up | Eye-level | Static | 70mm | Tripod | 2 J.D., 3 Lacey | 3 | J.D. silently fixes his gaze on Lacey, holding eye contact without responding.
Day 2 | 22:47 | 22:53 | 6 | Shot | 5 | 5.6 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium | Eye-level | Static | 50mm | Tripod | 2 J.D., 3 Lacey | 4 | Lacey looks directly at J.D., tilting her head in disbelief across the table.
Day 2 | 22:53 | 23:05 | 12 | Shot | 5 | 5.8 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium Long | Eye-level | Slow tracking | 35mm | Steady cam | 1 Erica, 2 J.D., 3 Lacey | 5 | J.D. turns from the table and walks away across the back room, leaving Lacey and Erica seated behind him. | J.D. walks away. Lacey (Heather) wraps after this.
Day 2 | 23:05 | 23:13 | 8 | Shot | 3 | 3.1 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium | Eye-level | Static | 35mm | Tripod | 1 Erica | 7 | Erica sits at a cluttered desk in the cramped back office, holding a phone to her ear. She glances toward the whiteboard with the safety message and the org chart taped beside it. | Clean whiteboard for the time jump back to 10:14 AM.
Day 2 | 23:13 | 23:21 | 8 | Shot | 3 | 3.2 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium Close-up | Eye-level | Slow push-in | 50mm | Steady cam | 1 Erica | 8 | Erica lowers her smile into a controlled expression and straightens in her chair, still holding the phone. Her eyes focus ahead toward an unseen point as she finishes the call.
Day 2 | 23:21 | 23:29 | 8 | Shot | 3 | 3.3 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium Two-shot | Eye-level | Static | 35mm | Tripod | 1 Erica, 2 J.D. | 6 | Erica sets the phone down on the desk and exhales, her shoulders dropping slightly. In the doorway behind her, J.D. stands motionless, already watching her.
Day 2 | 23:29 | 23:38 | 9 | Shot | 3 | 3.4 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium Two-shot | Eye-level | Slight handheld sway | 40mm | Handheld | 1 Erica, 2 J.D., 3 Lacey | 12 | Erica swivels slightly in her chair toward J.D., gesturing lightly with one hand as she explains. J.D. leans on the doorframe, listening intently.
Day 2 | 23:38 | 23:47 | 9 | Shot | 3 | 3.5 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium | Eye-level | Slow pan following marker | 35mm | Tripod | 1 Erica, 2 J.D., 3 Lacey | 12 | J.D. stands at the whiteboard and draws a rough top-down layout of the store with bold marker strokes. Erica watches from her chair, turned toward the board. | J.D. draws store layout.
Day 2 | 23:47 | 23:55 | 8 | Shot | 3 | 3.6 | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | Back room / office | INT | Medium Two-shot | Eye-level | Slow push-in | 50mm | Steady cam | 1 Erica, 2 J.D. | 10 | Erica looks back at J.D. with a skeptical expression, her head tilted slightly. J.D. faces her defensively, his posture tense and insistent.
Day 2 | 23:55 | 0:00 | 5 | Wrap |  |  | Black Rifle Coffee Company: San Antonio (Bitters Rd) · 180 W Bitters Rd, San Antonio, TX 78216 | [8 empty] | 0 | Wrap · Load-out
Day 2 |  |  | 360 | Total |  | 27 | [9 empty] | 234 | Day 2 total: setups and screen time

## Cast Calls
Day | Cast # | Character | Played by | Call (H/MU) | On set | Wrap | Hours on call
Day 1 | 3 | Lacey | Heather | 18:00 | 19:05 | 23:45 | 5.75
Day 1 | 4 | Bruce | Caleb | 18:00 | 19:05 | 23:45 | 5.75
Day 1 | 5 | Garrett | Casting TBD | 18:00 | 19:05 | 23:45 | 5.75
Day 1 | 1 | Erica | Nikki | 20:15 | 21:45 | 23:45 | 3.5
Day 1 | 2 | J.D. | Brent | 20:15 | 21:45 | 23:45 | 3.5
Day 1 | BG | Background (4 customers) | Extras | 18:30 | 19:05 | 19:55 | 1.42
Day 2 | 1 | Erica | Nikki | 18:00 | 18:30 | 23:55 | 5.92
Day 2 | 2 | J.D. | Brent | 18:00 | 18:30 | 23:55 | 5.92
Day 2 | 3 | Lacey | Heather | 18:00 | 18:30 | 23:05 | 5.08
Day 2 | 4 | Bruce | Caleb | 18:00 | 18:30 | 21:25 | 3.42
Hours on call = Wrap − Call, in hours.

## Cast Legend
Cast # | Character | Played by | Lines | Scenes
1 | Erica | Nikki | 29 | 3, 4, 5, 6, 7
2 | J.D. | Brent | 18 | 3, 4, 5, 6, 7
3 | Lacey | Heather | 21 | 2, 4, 5, 6, 7
4 | Bruce | Caleb | 10 | 2, 4, 6, 7
5 | Garrett | Casting TBD | 6 | 2, 7
6 | Evan (V.O.) | Casting TBD | 5 | 7
Evan is voice-only (off-camera); record separately.

## Art Department
ART DEPARTMENT: WARDROBE, PROPS & SET DRESSING
Story Day 1 = Scenes 2–6 · Next morning = Scene 7. Each principal needs two changes. Built from the script, shot list and storyboards.
How to use: the Status column (light yellow) is yours to fill in. Pick Need / Sourced / Rented / Pulled / On Set from the dropdown. Example: "Rented".
WARDROBE
Character | Cast # | Look | Scenes | Item | Storyboard ref | Notes | Status
Erica | 1 | Change 1 · Story Day 1 | 2–6 | Fitted black blazer | 3.2, 4.7 | Reads 'corporate executive in a coffee shop.' Most polished person in the building.
Erica | 1 | Change 1 · Story Day 1 | 2–6 | Black blouse / shell top
Erica | 1 | Change 1 · Story Day 1 | 2–6 | Dark tailored slacks
Erica | 1 | Change 1 · Story Day 1 | 2–6 | Black low heels or flats
Erica | 1 | Change 1 · Story Day 1 | 2–6 | BRCC GM name badge
Erica | 1 | Change 1 · Story Day 1 | 2–6 | Hair: loose, voluminous curls
Erica | 1 | Change 2 · Next morning | 7 | Second blazer or same blazer with a new top (different color under-layer) | 7.2, 7.9 | Needs to read as a new day. Change the top at minimum.
Erica | 1 | Change 2 · Next morning | 7 | Same slacks/shoes OK
Erica | 1 | Change 2 · Next morning | 7 | GM name badge
J.D. | 2 | Change 1 · Story Day 1 | 3–6 | Plate-carrier style vest (empty plates, no live gear) | 3.5, 6.1 | Wears a vest to work at a coffee shop. Played straight, never winking.
J.D. | 2 | Change 1 · Story Day 1 | 3–6 | Multicam / OCP-pattern combat shirt or tee
J.D. | 2 | Change 1 · Story Day 1 | 3–6 | Tan or coyote work pants / tactical pants
J.D. | 2 | Change 1 · Story Day 1 | 3–6 | Tan combat boots
J.D. | 2 | Change 1 · Story Day 1 | 3–6 | Flag/unit patch on vest
J.D. | 2 | Change 1 · Story Day 1 | 3–6 | Watch (G-Shock style)
J.D. | 2 | Change 1 · Story Day 1 | 3–6 | Assistant GM name tag
J.D. | 2 | Change 2 · Next morning | 7 | Same vest | 7.9 | Swap the shirt only. The vest is his identity.
J.D. | 2 | Change 2 · Next morning | 7 | Different shirt (solid coyote/OD tee)
J.D. | 2 | Change 2 · Next morning | 7 | Same pants/boots
Lacey | 3 | Change 1 · Story Day 1 | 2, 4–6 | Black fitted tee or tank | 2.4, 6.3 | Gun nerd, zero authority respect. Apron is the uniform; the attitude is the costume.
Lacey | 3 | Change 1 · Story Day 1 | 2, 4–6 | Black BRCC barista apron
Lacey | 3 | Change 1 · Story Day 1 | 2, 4–6 | Black jeans / work pants
Lacey | 3 | Change 1 · Story Day 1 | 2, 4–6 | Black boots or sneakers
Lacey | 3 | Change 1 · Story Day 1 | 2, 4–6 | Barista name tag
Lacey | 3 | Change 1 · Story Day 1 | 2, 4–6 | Hair: single side braid
Lacey | 3 | Change 1 · Story Day 1 | 2, 4–6 | Visible sleeve tattoos (Heather's own)
Lacey | 3 | Change 2 · Next morning | 7 | Different black or charcoal top | 7.3, 7.8 | Index card in apron pocket.
Lacey | 3 | Change 2 · Next morning | 7 | Same apron
Lacey | 3 | Change 2 · Next morning | 7 | Same braid (continuity)
Bruce | 4 | Change 1 · Story Day 1 | 2, 4, 6 | Plaid flannel shirt (red/brown/black) | 2.8, 4.5, 6.4 | Big, soft, approachable. Tool belt stays on in nearly everything.
Bruce | 4 | Change 1 · Story Day 1 | 2, 4, 6 | Black crew tee underneath
Bruce | 4 | Change 1 · Story Day 1 | 2, 4, 6 | Work jeans or Carhartt pants
Bruce | 4 | Change 1 · Story Day 1 | 2, 4, 6 | Work boots
Bruce | 4 | Change 1 · Story Day 1 | 2, 4, 6 | Tool belt w/ hammer, screwdrivers, tape measure
Bruce | 4 | Change 1 · Story Day 1 | 2, 4, 6 | Yellow rubber dish gloves (Sc 6)
Bruce | 4 | Change 2 · Next morning | 7 | Different flannel or same flannel over a different tee | 7.4, 7.7 | Ski mask must roll up cleanly for 7.7. Get 2 in case of snag.
Bruce | 4 | Change 2 · Next morning | 7 | Black knit ski mask, roll-up style
Bruce | 4 | Change 2 · Next morning | 7 | Tool belt (script: 'still wearing his tool belt')
Garrett | 5 | Change 1 · Story Day 1 | 2 | Golf polo (pastel or patterned) | 2.3, 2.6 | Script look is 'tactical vest over a golf polo.' The storyboard shows a waxed jacket. Pick one before the fitting.
Garrett | 5 | Change 1 · Story Day 1 | 2 | Tactical vest worn over the polo
Garrett | 5 | Change 1 · Story Day 1 | 2 | Khaki or golf slacks
Garrett | 5 | Change 1 · Story Day 1 | 2 | Belt sturdy enough for OWB holster
Garrett | 5 | Change 1 · Story Day 1 | 2 | OWB holster for 1911, worn 'prominently' on hip
Garrett | 5 | Change 1 · Story Day 1 | 2 | Sunglasses on collar or hat (optional)
Garrett | 5 | Change 2 · Next morning | 7 | Different golf polo | 7.1, 7.6 | Enters 'chest out.' Must be able to walk backwards with hands raised comfortably.
Garrett | 5 | Change 2 · Next morning | 7 | Same vest
Garrett | 5 | Change 2 · Next morning | 7 | Same holster + 1911
Garrett | 5 | Change 2 · Next morning | 7 | Same slacks OK
Background | BG | 4 customers in line | 2 | Customer 1: veteran type, BRCC hat, tee | 2.2, 2.5 | No logos except BRCC. Avoid white and loud patterns. Bring a second option each.
Background | BG | 4 customers in line | 2 | Customer 2: active-duty look, uniform or PT gear
Background | BG | 4 customers in line | 2 | Customer 3: office worker, button-down
Background | BG | 4 customers in line | 2 | Customer 4: casual, hoodie
PROPS
Category | Hero? | Item | Qty | Scenes | Used by | Notes | Status
Weapons (armorer) | HERO | 1911 pistol: non-firing replica or rubber stunt version | 2 | 2, 7 | Garrett | Hero plus backup. Must sit in the OWB holster; the hand hovers over it in 7.5. Armorer controls it at all times.
Weapons (armorer) | HERO | AK-pattern rifle: non-firing replica | 1 (+1 rubber) | 7 | Bruce | Raised on entrance (7.4). Rubber version for any rough handling. Cold check before every take.
Weapons (armorer) | HERO | OWB holster for 1911 | 1 | 2, 7 | Garrett | Listed under wardrobe too. Confirm fit with the replica.
Wardrobe props | HERO | Black knit ski mask (roll-up) | 2 | 7 | Bruce | Pushed up in 7.7.
Wardrobe props | HERO | Tool belt, loaded | 1 | 2, 4, 6, 7 | Bruce | Hammer, screwdrivers, tape measure, zip ties.
Wardrobe props | HERO | Yellow rubber gloves | 2 pr | 6 | Bruce | Peeled off on entrance (6.4).
Wardrobe props |  | Name badges: Erica (GM), J.D. (Asst GM), Lacey, Bruce | 1 each (+1 spare) | 2–7 | Staff | BRCC style.
Café: counter | HERO | Takeout cups printed 'GARRETT (ARMED)' | 12 | 2 | Lacey | Insert 2.7. Lacey writes on camera, so bring blanks plus pre-written backups.
Café: counter |  | Black Sharpie / cup marker | 3 | 2 | Lacey
Café: counter |  | Medium lavender oat milk latte: hero drink | 4 | 2 | Garrett | Half-caf, heavy foam. Refresh for continuity.
Café: counter | HERO | Wall clock, hands manually settable | 1 | 2, 7 | — | Set to 9:11 (Sc 2, insert 2.1) and 9:59 (Sc 7). Swap for the location clock or set its hands.
Café: counter | HERO | Store phone with speakerphone | 1 | 3, 7 | Erica | Landline-style. Back office in Sc 3, counter in Sc 7. Evan's V.O. plays through it.
Café: counter | HERO | Index cards: Lacey's apology | 10 | 7 | Lacey | Dropped, picked up and torn every take (7.8).
Café: counter |  | Cash register / POS | 1 | 2 | Lacey | Use location POS. Lock out any live screens.
Café: counter |  | Coffee brewing: practical espresso machine + drip | — | 7 | — | Location equipment. Espresso machine hisses in the silence after Erica's line (Sc 4).
Café: counter |  | Door chime / bell | 1 | 7 | — | Sound can add it in post. Practical is nice to have.
Café: floor |  | Step stool or 4-ft ladder | 1 | 2 | Bruce | Bruce stands on it (2.2, 2.8). Safety-check weight rating.
Café: floor |  | Removable ceiling tile (or hero tile panel) | 1 | 2 | Bruce | Bruce is fixing it in the background.
Café: floor | HERO | Mop + bucket (wringer) | 1 | 4 | Bruce | Mops the same tile the whole scene. Leaned on counter in 4.6.
Back room / office |  | Desk + office chair (swivel) | 1 | 3, 5 | Erica | Erica swivels in 3.4.
Back room / office |  | Small table + 3 chairs | 1 set | 5 | Erica, Lacey, J.D. | 'Deposition' setup (5.1).
Back room / office | HERO | Whiteboard reading 'SAFETY IS EVERYONE'S JOB' (faded) | 1 | 3 | — | Same board J.D. draws the store layout on in 3.5.
Back room / office | HERO | Printed BRCC org chart with Erica's face glued over 'Regional Manager' | 2 | 3 | — | Taped beside the whiteboard. Visual gag, so make it legible on a 35mm medium.
Back room / office |  | Syrup boxes, cases of cups, mini fridge | Dressing | 3, 5 | — | Cramped, cluttered office.
Back room / office |  | Dry-erase markers (black, red, blue) + eraser | 2 sets | 3, 6 | J.D. | Clean the board between takes of 3.5.
Break area | HERO | Whiteboard: 'PROPOSED COURSES OF ACTION' + COA 1–4 | 1 | 6 | J.D. | COA 1: Lacey apologizes to Garrett · COA 2: Erica apologizes to Bruce · COA 3: Both · COA 4: Neither.
Break area | HERO | Napkins + pen for apology drafts | 1 pack | 6 | Lacey | Held up to camera in 6.3. Pre-letter a few hero napkins.
Break area |  | Granola bars | 6 | 6 | Bruce | Mid-bite in 6.6 and swallowed. Bring extras for retakes.
Break area |  | Break table, chairs, counter, microwave, mugs | Dressing | 6 | — | Location break room.
Vehicles |  | Garrett's pickup truck | 1 | 7 (optional) | Garrett | Only if the peel-out pickup is shot. Not on the shot list.
Exterior |  | American flag on pole | 1 | 1 | — | Location flag. Confirm it's up and lit for the night shoot.
Total props |  | 31 |  |  | Hero props | 15
SET DRESSING
Area |  | Item |  |  |  | Notes | Status
Café floor |  | Military & Americana decor: flags, unit patches, framed photos |  |  |  | Mostly in place at Bitters Rd. Add pieces if frame 2.2 needs them.
Café floor |  | 4 background customers in line |  |  |  | See wardrobe.
Windows (Sc 1, 2, 7) |  | Diffusion / day-look treatment on front windows |  |  |  | Night-for-day: see Camera & Equipment → Lighting.
Back room |  | Cramped office clutter |  |  |  | Syrup boxes, mini fridge, filing, paperwork, BRCC bags.
All |  | Clear/cover any live screens, posted schedules, staff personal info |  |  |  | Location courtesy and clearance.

## Camera & Equipment
CAMERA & EQUIPMENT: LENSES, CAMERA SUPPORT, LIGHTING, GRIP & SOUND
Built from the shot list (lens, rig and movement for all 47 live-action setups). Interiors in Scenes 2, 4 and 7 are night-for-day.
How to use: the Status column (light yellow) is yours to fill in. Pick Need / Sourced / Rented / Pulled / On Set from the dropdown. Example: "Rented".
LENS PLAN (counts update from the Shooting Schedule tab)
Focal length | # Shots | Shots
24mm | 3 | 1.1, 2.2, 7.4
28mm | 2 | 4.1, 7.1
32mm | 3 | 4.6, 6.5, 7.9
35mm | 14 | 1.3, 2.3, 3.1, 3.3, 3.5, 4.2, 4.4, 5.1, 5.8, 6.1, 6.3, 6.4, 7.2, 7.6
40mm | 8 | 2.8, 3.4, 4.3, 4.7, 6.2, 6.6, 7.3, 7.7
45mm | 1 | 7.8
50mm | 12 | 1.2, 2.4, 2.5, 3.2, 3.6, 4.5, 5.2, 5.3, 5.4, 5.5, 5.6, 7.5
60mm | 1 | 2.7
65mm | 1 | 2.6
70mm | 1 | 5.7
85mm | 1 | 2.1
Total | 47
Rig split
Steadicam / gimbal | 33
Tripod | 9
Handheld | 5
EQUIPMENT LIST
Category | Qty | Item | Used for | Notes | Status
Camera | 1 | Cinema camera body, A-cam (4K+, 16:9, strong low-light / dual native ISO) | All scenes | Night shoot. Pick a body that's clean at high base ISO.
Camera | 1 | B-cam body (matching sensor/color) | Sc 4, 6, 7 | Recommended. Cross-shoot the big group dialogue scenes to fit 27 setups into Day 2.
Camera | 8 cards | Media cards + readers | — | Offload & back up at meal and wrap.
Camera | 12 | Batteries (V-mount/Gold) + chargers | — | 6-hr nights with Steadicam draw.
Camera | 1 per cam | Matte box, follow focus (wireless), 7" on-board monitor | —
Camera | 1 kit | Wireless video TX/RX + director's monitor (video village) | — | Director + script supervisor at the monitor.
Lenses | 1 set | Matched cine prime set: 24, 28, 35, 40, 50, 65, 85mm | 41 of 47 live-action shots | e.g. Sigma Cine FF High Speed or equivalent. 35mm and 50mm do the heavy lifting (26 shots).
Lenses | 1 | 32mm prime (or use 35mm) | 4.6, 6.5, 7.9 | Optional. 35mm covers these if the set has no 32.
Lenses | 1 | Short cine zoom, ~28–80mm range | 7.8 (45mm), 5.7 (70mm), fast resets | Covers the in-between focal lengths and speeds up resets on Steadicam.
Lenses | 1 | Close-focus solution: +1/+2 diopter or 60mm macro | 2.7 cup insert, 2.1 clock | Cup lettering needs to be tack sharp.
Lenses | 1 set | Filters: 1/8 & 1/4 diffusion (Pro-Mist/Glimmerglass), ND set, polarizer | All | Soft halation for the moody storyboard look. Polarizer for window glare.
Support | 1 | Steadicam rig + operator (or Ronin-2 class gimbal) | 34 shots | Most of the shot list is 'Steady cam'. Book an operator.
Support | 1 | Tripod: 100mm bowl, fluid head, sticks + baby legs + hi-hat | Sc 3, 5 (9 shots), inserts | Hi-hat for the cup insert.
Support | 1 | Handheld / shoulder rig | 3.4, 4.5, 6.3, 6.6, 7.4 | Quick handheld pan on the AK entrance.
Support | 1 | Dolly or slider (optional) | Push-ins (13 shots) | Steadicam can do the push-ins. A slider makes the inserts repeatable.
Lighting | 2 | Large daylight LED or 1.2K HMI outside front windows | Sc 2, 4, 7 (night-for-day) | Fakes morning sun through the storefront glass.
Lighting | 2 | Mid-power LED COB (600W class, bi-color) | Key sources, bounced or through diffusion | Soft key for counter coverage.
Lighting | 2 | Mid-power LED COB (300W class) | Back room, break area, fill | Smaller rooms, Day 2.
Lighting | 6 | LED tube lights (RGB, battery) | Practical augment, edge/hair light, hide-in-set | Hide behind the counter, shelves and window frames.
Lighting | 3 | Flexible LED mats / small panels | Back office (Sc 3, 5), tight corners | Low-profile ceiling bounce in the cramped office.
Lighting | Location | Practicals: café pendants, menu boards, office desk lamp | All interiors | Dim pendants to taste. Keep the warm 'coffee shop' glow.
Lighting | 2 | Small fresnel / LED spot | Clock insert, logo window (1.3), eye lights | Shape the clock face and the cup.
Lighting | 1 | Exterior: 600W LED + battery for storefront/flag | Sc 1 | Fill if the sun is gone. Flag needs a light at night anyway.
Grip | 12 | C-stands | —
Grip | 4 | Combo / roller stands | — | For the window units.
Grip | 24 | Sandbags | — | Every stand bagged in a public café.
Grip | 1 kit | 8x8 frame + 1/2 grid cloth, Ultrabounce, Full Silk | Window diffusion, big soft key
Grip | 1 kit | 4x4 floppies, 24x36 flags, cutters, solids | Control spill in small rooms
Grip | 1 each | Diffusion & gel rolls: 216, 250, CTB/CTO, ND .3/.6 | Windows, practicals | Gel the practicals or windows to balance.
Grip | 1 kit | Apple boxes (full set), wedges, clamps, A-clamps | —
Electric | 20 | Stingers / extension cables (12/3) | — | Map the café's circuits before Day 1.
Electric | 1 | Power distro / quiet inverter generator | Window units | 1.2K HMIs or big LEDs can trip café circuits. Plan dedicated power.
Sound | 1 | Boom mic + boom pole + blimp | All dialogue
Sound | 6 | Wireless lav kits | Principals + Garrett
Sound | 1 | Field recorder with timecode | — | Jam sync with camera.
Sound | 1 | Playback speaker for Evan scratch V.O. | 7.9 | Phone gag timing. Final V.O. recorded separately.
Sound | — | Room tone + wild lines | Each set | 30 sec room tone per set before moving.
Set ops | 8 | Comms (walkies + surveillance earpieces) | —
Set ops | 1 | Monitors cart, director's chairs, script-sup kit | —